## Cover
WADJET GRC — RISK REGISTER & MITIGATION PLAN
Confidential ¦ Version 1.0 ¦ Date: 2026-06-06 ¦ Prepared by: Cybersecurity / GRC Function
Total Risks | Critical |  | High | Total Budget | Est. Loss
48 | 11 |  | 34 | $4.275M | $109M
WORKBOOK CONTENTS
Document Information |  | Organisation metadata and classification
Risk Methodology |  | Scoring matrix and escalation thresholds
Risk Register |  | Full 48-risk inventory with scores and existing controls
Mitigation Plan |  | Detailed action plans, owners, budgets, RAG status per risk
Summary Dashboard |  | Executive overview by category, budget, and estimated loss
Risk Methodology Ref |  | Likelihood & impact scale reference card
RAG STATUS LEGEND
🟢 Green |  | On track — all actions progressing as planned
🟡 Amber |  | Minor delay — at risk but recoverable
🔴 Red |  | Escalation required — immediate action needed

## Document Information
DOCUMENT INFORMATION
Wadjet GRC Platform — Risk Register & Mitigation Plan
Field | Value
Organization | (Enter organisation name)
Sector | (e.g. Banking & Financial Services)
Scope | (e.g. Enterprise-wide Cybersecurity & GRC)
Classification | Confidential
Version | 1.0
Date | 2026-06-06
Prepared By | Cybersecurity / GRC Function
Approved By | Plant Management / Risk Committee
ℹ️ Fill in the highlighted cells (Organisation, Sector, Scope) before distributing this document.

## Risk ID Checklist – EN
RISK IDENTIFICATION CHECKLIST — ENGLISH
Use this checklist to identify potential risks across all organisational domains ¦ Tick all that apply
# | Risk Category | Risk Question / Checklist Item | Yes | No | Partially | Notes
CYBERSECURITY
1 | CYBERSECURITY | Is there a risk of phishing or social engineering attacks on employees?
2 | CYBERSECURITY | Is there a risk of ransomware or malware infecting endpoints?
3 | CYBERSECURITY | Are critical systems at risk from unpatched vulnerabilities?
4 | CYBERSECURITY | Is there a risk of unauthorized access to privileged accounts?
5 | CYBERSECURITY | Is there a risk of credential stuffing or brute force attacks?
6 | CYBERSECURITY | Is network segmentation insufficient to prevent lateral movement?
7 | CYBERSECURITY | Is there a risk from API vulnerabilities in digital services?
INFORMATION SECURITY
8 | INFORMATION SECURITY | Is there a risk of sensitive customer data leakage?
9 | INFORMATION SECURITY | Are databases at risk of misconfiguration or unauthorised access?
10 | INFORMATION SECURITY | Is there a risk of insider threats from employees with elevated access?
11 | INFORMATION SECURITY | Is multi-factor authentication (MFA) not enforced across all systems?
12 | INFORMATION SECURITY | Is there a risk from misuse of privileged or administrative accounts?
COMPLIANCE & LEGAL
13 | COMPLIANCE & LEGAL | Is there a risk of non-compliance with CBE regulations?
14 | COMPLIANCE & LEGAL | Is there a risk of violating data residency requirements (PDPL)?
15 | COMPLIANCE & LEGAL | Is there a risk of failing to report a breach within 72 hours (PDPL)?
16 | COMPLIANCE & LEGAL | Are Data Protection Impact Assessments (DPIAs) not being conducted?
17 | COMPLIANCE & LEGAL | Is the Data Protection Officer (DPO) formally appointed and registered?
18 | COMPLIANCE & LEGAL | Are Records of Processing Activities (ROPA) maintained and up to date?
19 | COMPLIANCE & LEGAL | Is there a risk of cross-border data transfers without regulatory approval?
OPERATIONAL & BCP
20 | OPERATIONAL & BCP | Is there a risk of backup failure or inability to restore systems?
21 | OPERATIONAL & BCP | Has a Business Continuity Plan (BCP) been tested recently?
22 | OPERATIONAL & BCP | Are unauthorized system changes a risk due to weak change controls?
23 | OPERATIONAL & BCP | Is there a risk of service outage from digital resilience test failures?
24 | OPERATIONAL & BCP | Are automated workflows at risk of failure affecting audit evidence?
THIRD PARTY RISK
25 | THIRD PARTY RISK | Is there a risk of a security breach through a vendor or supplier?
26 | THIRD PARTY RISK | Are third-party data processing agreements (DPAs) in place?
27 | THIRD PARTY RISK | Is there excessive dependency on a single cloud or ICT provider?
28 | THIRD PARTY RISK | Are software supply chain risks managed (open-source libraries, SBOMs)?
29 | THIRD PARTY RISK | Is there a formal vendor security assessment program?
HUMAN RISK
30 | HUMAN RISK | Is employee security awareness training conducted regularly?
31 | HUMAN RISK | Is there a risk from vishing (voice-based social engineering) attacks?
32 | HUMAN RISK | Is there a risk from AI-generated deepfake social engineering?
33 | HUMAN RISK | Are insider threat detection controls (UEBA) in place?
APPLICATION & MOBILE SECURITY
34 | APPLICATION & MOBILE SECURITY | Is the mobile banking application protected against reverse engineering?
35 | APPLICATION & MOBILE SECURITY | Is there a risk from mobile banking trojans on customer devices?
36 | APPLICATION & MOBILE SECURITY | Are open banking APIs secured with gateway, WAF and rate limiting?
CLOUD, PHYSICAL & AI
37 | CLOUD, PHYSICAL & AI | Are cloud resources at risk of misconfiguration (public buckets)?
38 | CLOUD, PHYSICAL & AI | Is there a risk of physical breach to the data centre?
39 | CLOUD, PHYSICAL & AI | Is there a risk of ATM skimming or card fraud?
40 | CLOUD, PHYSICAL & AI | Are employees exposing sensitive data through public AI tools?
RISK MANAGEMENT & GRC
41 | RISK MANAGEMENT & GRC | Are risk scores and heatmaps calculated and validated correctly?
42 | RISK MANAGEMENT & GRC | Is compliance framework mapping accurate and reviewed regularly?

## Risk ID Checklist – AR
قائمة التحقق من تحديد المخاطر — عربي
استخدم هذه القائمة لتحديد المخاطر المحتملة في جميع مجالات المنظمة ¦ ضع علامة على كل ما ينطبق
# | فئة المخاطر | سؤال التحقق / البند | نعم | لا | جزئياً | ملاحظات
الأمن السيبراني
1 | الأمن السيبراني | هل هناك خطر من هجمات التصيد الاحتيالي أو الهندسة الاجتماعية على الموظفين؟
2 | الأمن السيبراني | هل هناك خطر إصابة الأجهزة بالفدية أو البرمجيات الخبيثة؟
3 | الأمن السيبراني | هل الأنظمة الحيوية معرضة للخطر بسبب ثغرات غير مُرقَّعة؟
4 | الأمن السيبراني | هل هناك خطر من وصول غير مصرح به إلى الحسابات ذات الامتيازات؟
5 | الأمن السيبراني | هل هناك خطر من هجمات حشو بيانات الاعتماد أو القوة الغاشمة؟
6 | الأمن السيبراني | هل تجزئة الشبكة غير كافية للحد من التحرك الأفقي؟
7 | الأمن السيبراني | هل هناك خطر من ثغرات واجهات برمجة التطبيقات (API) في الخدمات الرقمية؟
أمن المعلومات
8 | أمن المعلومات | هل هناك خطر من تسريب بيانات العملاء الحساسة؟
9 | أمن المعلومات | هل قواعد البيانات معرضة للخطر بسبب إعدادات خاطئة أو وصول غير مصرح به؟
10 | أمن المعلومات | هل هناك خطر من تهديدات داخلية من موظفين يتمتعون بصلاحيات مرتفعة؟
11 | أمن المعلومات | هل لم يتم فرض المصادقة متعددة العوامل (MFA) على جميع الأنظمة؟
12 | أمن المعلومات | هل هناك خطر من إساءة استخدام الحسابات ذات الامتيازات أو الإدارية؟
الامتثال والشؤون القانونية
13 | الامتثال والشؤون القانونية | هل هناك خطر من عدم الامتثال للوائح البنك المركزي المصري؟
14 | الامتثال والشؤون القانونية | هل هناك خطر من انتهاك اشتراطات إقامة البيانات (قانون حماية البيانات الشخصية)؟
15 | الامتثال والشؤون القانونية | هل هناك خطر من عدم الإبلاغ عن الاختراق خلال 72 ساعة؟
16 | الامتثال والشؤون القانونية | هل يتم إجراء تقييمات أثر حماية البيانات (DPIA) عند اللزوم؟
17 | الامتثال والشؤون القانونية | هل تم تعيين وتسجيل مسؤول حماية البيانات (DPO) رسمياً؟
18 | الامتثال والشؤون القانونية | هل يتم الاحتفاظ بسجلات أنشطة المعالجة (ROPA) ومراجعتها بانتظام؟
19 | الامتثال والشؤون القانونية | هل هناك خطر من نقل البيانات عبر الحدود دون موافقة تنظيمية؟
المخاطر التشغيلية وخطط الاستمرارية
20 | المخاطر التشغيلية وخطط الاستمرارية | هل هناك خطر من فشل النسخ الاحتياطي أو عدم القدرة على استعادة الأنظمة؟
21 | المخاطر التشغيلية وخطط الاستمرارية | هل تم اختبار خطة استمرارية الأعمال (BCP) مؤخراً؟
22 | المخاطر التشغيلية وخطط الاستمرارية | هل التغييرات غير المصرح بها مخاطرة بسبب ضعف إجراءات إدارة التغيير؟
23 | المخاطر التشغيلية وخطط الاستمرارية | هل هناك خطر من انقطاع الخدمة نتيجة إخفاق اختبارات المرونة الرقمية؟
24 | المخاطر التشغيلية وخطط الاستمرارية | هل سير العمل الآلية معرضة لأعطال تؤثر على أدلة التدقيق؟
مخاطر الأطراف الثالثة
25 | مخاطر الأطراف الثالثة | هل هناك خطر من اختراق أمني عبر مورد أو مزود خدمة؟
26 | مخاطر الأطراف الثالثة | هل اتفاقيات معالجة البيانات (DPA) مع الأطراف الثالثة مُبرمة؟
27 | مخاطر الأطراف الثالثة | هل هناك اعتماد مفرط على مزود سحابة أو خدمات تقنية واحد؟
28 | مخاطر الأطراف الثالثة | هل يتم إدارة مخاطر سلسلة توريد البرمجيات (المكتبات مفتوحة المصدر، SBOM)؟
29 | مخاطر الأطراف الثالثة | هل يوجد برنامج رسمي لتقييم أمن الموردين؟
المخاطر البشرية
30 | المخاطر البشرية | هل يتم إجراء تدريب منتظم للتوعية الأمنية للموظفين؟
31 | المخاطر البشرية | هل هناك خطر من هجمات التصيد الصوتي (Vishing)؟
32 | المخاطر البشرية | هل هناك خطر من هجمات الهندسة الاجتماعية باستخدام التزييف العميق (Deepfake)؟
33 | المخاطر البشرية | هل ضوابط اكتشاف التهديدات الداخلية (UEBA) مطبقة؟
أمن التطبيقات والهواتف المحمولة
34 | أمن التطبيقات والهواتف المحمولة | هل تطبيق الهاتف المحمول محمي من الهندسة العكسية؟
35 | أمن التطبيقات والهواتف المحمولة | هل هناك خطر من إصابة أجهزة العملاء ببرامج التجسس المصرفية؟
36 | أمن التطبيقات والهواتف المحمولة | هل واجهات برمجة التطبيقات المصرفية مؤمنة بـ API Gateway وجدار حماية ومعدل طلبات محدود؟
السحابة والأمن المادي والذكاء الاصطناعي
37 | السحابة والأمن المادي والذكاء الاصطناعي | هل الموارد السحابية معرضة لخطر الإعدادات الخاطئة (الحاويات العامة)؟
38 | السحابة والأمن المادي والذكاء الاصطناعي | هل هناك خطر من اختراق مادي لمركز البيانات؟
39 | السحابة والأمن المادي والذكاء الاصطناعي | هل هناك خطر من قرصنة أجهزة الصراف الآلي أو احتيال البطاقات؟
40 | السحابة والأمن المادي والذكاء الاصطناعي | هل يتسرب الموظفون ببيانات حساسة عبر أدوات الذكاء الاصطناعي العامة؟
إدارة المخاطر وحوكمة مخاطر الامتثال
41 | إدارة المخاطر وحوكمة مخاطر الامتثال | هل يتم حساب درجات المخاطر وخرائطها والتحقق منها بشكل صحيح؟
42 | إدارة المخاطر وحوكمة مخاطر الامتثال | هل رسم خرائط إطار الامتثال دقيق ويُراجع بانتظام؟

## Risk Methodology
RISK SCORING METHODOLOGY
Risk Score = Likelihood × Impact Range: 1 – 25
LIKELIHOOD SCALE |  |  | IMPACT SCALE
Score | Level | Description | Score | Level | Description
1 | Very Unlikely | Rarely occurs | 1 | Very Low | Minor disruption, negligible financial impact
2 | Unlikely | May occur once in 5+ years | 2 | Low | Limited disruption, minor financial impact, no safety impact
3 | Possible | May occur once in 1–5 years | 3 | Medium | Moderate disruption, significant financial impact, minor safety impact
4 | Likely | May occur annually | 4 | High | Major disruption, severe financial impact, moderate safety impact, reputational damage
5 | Very Likely | Expected to occur frequently | 5 | Critical | Catastrophic disruption, extreme financial loss, severe safety impact, regulatory non-compliance
OVERALL INHERENT RISK RATING
Score Range | Risk Level | Escalation Path
1 – 2 | Very Low | Managed at Operational Team Level
3 – 4 | Low | Managed by System / Asset Owner (e.g., IT Manager / Operations Manager)
5 – 10 | Medium | Escalate to Head of Department / Risk Management Team
12 – 16 | High | Escalate to C-Suite (CEO / CRO / CISO) via the GRC Committee
20 – 25 | Critical | Escalate to the Board of Directors via the Enterprise Risk Register (ERR)
ESCALATION FRAMEWORK
🔴 Score 20–25 CRITICAL |  | Escalate to the Board of Directors via the Enterprise Risk Register (ERR)
🟠 Score 12–16 HIGH |  | Escalate to C-Suite (CEO / CRO / CISO) via the GRC Committee
🟡 Score 5–10 MEDIUM |  | Escalate to Head of Department / Risk Management Team
🟢 Score 3–4 LOW |  | Managed by System / Asset Owner (e.g., IT Manager / Operations Manager)
🔵 Score 1–2 VERY LOW |  | Managed at Operational Team Level

## Risk Scoring Template
RISK SCORING TEMPLATE
Complete one template per risk assessed ¦ Risk Score = Likelihood × Impact
SECTION 1 — RISK IDENTIFICATION
Risk ID
Risk Title
Date Assessed
Assessed By
Risk Category
Asset / System
Risk Owner
SECTION 2 — RISK SCORING
Likelihood Scale → | 1 – Very Unlikely | 2 – Unlikely | 3 – Possible | 4 – Likely | 5 – Very Likely
Selected Likelihood (1–5)
Impact Scale → | 1 – Very Low | 2 – Low | 3 – Medium | 4 – High | 5 – Critical
Selected Impact (1–5)
RISK SCORE = Likelihood × Impact
RISK LEVEL | —
SECTION 3 — TREATMENT & OWNERSHIP
Recommended Action
Mitigation Description
Residual Likelihood
Residual Impact
Target Date
Review Frequency
SECTION 4 — NOTES & COMMENTS

## Risk Rigister
WADJET GRC — RISK REGISTER ¦ 48 Risks ¦ Confidential
RISK SCENARIO | [11 empty] | LIKELIHOOD | IMPACT DIMENSIONS | [7 empty] | RISK SCORING |  |  | CONTROL & RESIDUAL |  |  | TREATMENT & MITIGATION
Risk ID | Process | Sub-Process | Asset / System | Owner Team | Risk Category | Threat | Vulnerability | Severity | Risk Title | Risk Description | Risk Ref | Likelihood | Finance | Regulatory | Reputational | Safety | Operational | C | I | A | Overall Score | Risk Score | Inherent Level | Existing Controls | Residual Score | Overall Risk | Treatment | Status | Mitigation Actions | Deadline | Owner
R-001 | Information Security Management | Email Security | Microsoft Exchange | SOC Team | Cybersecurity | Phishing Attack | Lack of Security Awareness | High | Credential Theft Through Phishing | Employees may disclose credentials through phishing emails leading to unauthorized access. | R-001 | 5 | 3 | 4 | 4 | 1 | 4 | 5 | 4 | 3 | 20 | 20 | Critical | Email Gateway MFA Awareness Training | 10 | Medium | Mitigate | Open | Conduct quarterly phishing simulations and awareness campaigns | 2026-12-31 | SOC Manager
R-002 | Endpoint Security | Malware Protection | End User Devices | SOC Team | Cybersecurity | Ransomware | Unpatched Endpoints | Critical | Ransomware Attack | Malware encrypts business-critical data causing service disruption | R-002 | 4 | 5 | 4 | 5 | 1 | 5 | 4 | 5 | 5 | 20 | 20 | Critical | EDR, Antivirus, Backups | 12 | High | Mitigate | Open | Monthly vulnerability management and backup testing | 2026-12-12 | SOC Manager
R-003 | Access Management | Privileged Access Management | Active Directory | IAM Team | Information Security | Privilege Escalation | Excessive User Permissions | High | Unauthorized Privileged Access | Unauthorized users gain elevated privileges | R-003 | 4 | 4 | 5 | 4 | 1 | 4 | 5 | 5 | 3 | 16 | 16 | Critical | RBAC, MFA, Access Reviews | 8 | Medium | Mitigate | Open | Quarterly privileged access review | 2026-11-30 | IAM Manager
R-004 | Compliance Management | Regulatory Monitoring | Compliance Platform | Compliance Team | Compliance | Missing Regulatory Requirements | Lack of Continuous Monitoring | High | Regulatory Non-Compliance | Failure to comply with CBE or PCI DSS requirements | R-004 | 3 | 4 | 5 | 4 | 1 | 3 | 2 | 4 | 2 | 12 | 12 | High | Internal Audit, Compliance Reviews | 6 | Medium | Mitigate | Open | Continuous compliance monitoring | 2026-10-31 | Compliance Manager
R-005 | Data Protection | Data Handling | Customer Database | Data Governance Team | Information Security | Data Exposure | Misconfigured Permissions | Critical | Customer Data Leakage | Sensitive customer data may be exposed | R-005 | 3 | 5 | 5 | 5 | 1 | 3 | 5 | 4 | 2 | 15 | 15 | High | DLP, Encryption | 8 | Medium | Mitigate | Open | Access reviews and DLP tuning | 2026-12-31 | Data Protection Officer
R-006 | Third Party Risk Management | Vendor Assessment | Vendor Portal | TPRM Team | Third Party Risk | Supply Chain Attack | Weak Vendor Security | High | Third Party Security Breach | Vendor compromise affecting bank data | R-006 | 3 | 4 | 4 | 5 | 1 | 4 | 5 | 4 | 3 | 12 | 12 | High | Vendor Security Assessment | 6 | Medium | Mitigate | Open | Annual vendor reassessment | 2026-09-30 | Vendor Risk Manager
R-007 | Business Continuity | Backup Management | Backup Server | IT Operations | Operational | Backup Failure | Lack of Backup Validation | High | Backup and Recovery Failure | Inability to restore critical systems after an incident | R-007 | 3 | 4 | 3 | 3 | 1 | 5 | 2 | 4 | 5 | 12 | 12 | High | Daily Backup Jobs | 6 | Medium | Mitigate | Open | Quarterly restoration testing | 2026-11-30 | IT Operations Manager
R-008 | Human Resources Security | Employee Monitoring | Internal Systems | HR & Security | Information Security | Malicious Insider | Excessive Privileges | High | Insider Threat Activity | Employees misuse authorized access | R-008 | 3 | 4 | 4 | 4 | 1 | 4 | 5 | 4 | 3 | 12 | 12 | High | User Activity Monitoring | 6 | Medium | Mitigate | Open | User behavior analytics deployment | 2026-12-31 | Information Security Manager
R-009 | Vulnerability Management | Patch Management | Production Servers | IT Security Team | Cybersecurity | Exploitation of Vulnerabilities | Missing Security Updates | Critical | Unpatched Critical Vulnerability | Attackers exploit known vulnerabilities | R-009 | 4 | 4 | 4 | 4 | 1 | 5 | 5 | 5 | 4 | 16 | 16 | Critical | Monthly Patch Cycle | 8 | Medium | Mitigate | Open | Weekly vulnerability scans | 2026-10-31 | Vulnerability Management Lead
R-010 | Incident Management | Security Incident Handling | SIEM Platform | SOC Team | Operational | Delayed Incident Response | Lack of IR Procedures | High | Incident Response Failure | Security incidents are not contained in a timely manner | R-010 | 3 | 4 | 4 | 4 | 1 | 5 | 4 | 4 | 5 | 12 | 12 | High | Incident Response Plan | 6 | Medium | Mitigate | Open | Conduct tabletop exercises every quarter | 2026-12-31 | SOC Manager
R-011 | Access Management | Authentication Management | Identity Management System | IAM Team | Information Security | Credential Compromise | MFA Not Enforced | High | Absence of Multi-Factor Authentication | Attackers may gain unauthorized access using stolen credentials. | R-011 | 4 | 4 | 4 | 4 | 1 | 3 | 5 | 4 | 3 | 16 | 16 | Critical | Password Policy | 8 | Medium | Mitigate | Open | Enforce MFA for all users. | 2026-12-31 | IAM Manager
R-012 | Security Monitoring | Log Monitoring | SIEM Platform | SOC Team | Cybersecurity | Undetected Attack | Incomplete Log Collection | High | Failure to Detect Security Incidents | Security events may remain unnoticed due to insufficient monitoring. | R-012 | 3 | 4 | 4 | 4 | 1 | 5 | 4 | 4 | 5 | 12 | 12 | High | SIEM Monitoring | 6 | Medium | Mitigate | Open | Enable centralized logging and alert tuning. | 2026-11-30 | SOC Manager
R-013 | Data Governance | Data Retention | Customer Information Database | Compliance Team | Compliance | Regulatory Violation | Missing Retention Policy | High | Improper Data Retention Management | Failure to retain or dispose of data according to regulations. | R-013 | 3 | 3 | 5 | 4 | 1 | 3 | 4 | 3 | 2 | 12 | 12 | High | Data Classification Policy | 6 | Medium | Mitigate | Open | Implement retention and disposal procedures. | 2026-10-31 | Compliance Manager
R-014 | Business Continuity Management | Disaster Recovery | Core Banking Infrastructure | IT Operations | Business Continuity | Disaster Event | Untested Recovery Plan | Critical | Business Continuity Failure | Critical services may not recover after a major disruption. | R-014 | 3 | 5 | 4 | 5 | 1 | 5 | 3 | 4 | 5 | 15 | 15 | High | DR Site | 8 | Medium | Mitigate | Open | Perform annual DR testing. | 2026-12-31 | Business Continuity Manager
R-015 | Change Management | Change Approval | Production Systems | IT Operations | Operational | Unauthorized Changes | Weak Change Control Process | High | Unauthorized System Changes | Unapproved changes may disrupt business services. | R-015 | 3 | 3 | 3 | 3 | 1 | 5 | 2 | 5 | 4 | 9 | 9 | Medium | CAB Review Process | 4 | Low | Mitigate | Open | Enforce change approval workflow. | 2026-09-30 | Change Manager
R-016 | Database Security Management | Database Configuration | Customer Database | Database Administration Team | Information Security | Data Exposure | Misconfigured Database Settings | Critical | Database Security Misconfiguration | Sensitive data may become accessible due to incorrect settings. | R-016 | 3 | 5 | 5 | 5 | 1 | 3 | 5 | 4 | 2 | 15 | 15 | High | Secure Configuration Standards | 8 | Medium | Mitigate | Open | Quarterly database configuration review. | 2026-12-31 | Database Manager
R-017 | Privileged Access Management | Admin Account Management | Active Directory | IAM Team | Information Security | Insider Abuse | Lack of PAM Controls | High | Misuse of Privileged Accounts | Administrative accounts may be abused intentionally or accidentally. | R-017 | 3 | 4 | 4 | 4 | 1 | 4 | 5 | 5 | 3 | 12 | 12 | High | Access Review | 6 | Medium | Mitigate | Open | Implement PAM solution. | 2026-12-31 | IAM Manager
R-018 | Vulnerability Management | Remediation Tracking | Enterprise Servers | Vulnerability Management Team | Cybersecurity | Vulnerability Exploitation | Delayed Patch Deployment | High | Delayed Vulnerability Remediation | Known vulnerabilities remain exposed for extended periods. | R-018 | 4 | 4 | 4 | 4 | 1 | 4 | 5 | 5 | 4 | 16 | 16 | Critical | Monthly Patch Cycle | 8 | Medium | Mitigate | Open | Weekly remediation tracking. | 2026-10-31 | Vulnerability Management Lead
R-019 | Security Awareness Program | Employee Training | Workforce | HR & Security Team | Human Risk | Social Engineering | Lack of Security Training | High | Insufficient Security Awareness | Employees may fall victim to social engineering attacks. | R-019 | 4 | 3 | 3 | 4 | 1 | 4 | 4 | 3 | 3 | 12 | 12 | High | Annual Training | 6 | Medium | Mitigate | Open | Conduct quarterly awareness campaigns. | 2026-12-31 | Security Awareness Lead
R-020 | Third Party Risk Management | Vendor Data Management | Vendor Integrated Systems | TPRM Team | Third Party Risk | Vendor Breach | Weak Vendor Security Controls | High | Third Party Data Exposure | Customer data may be exposed through a compromised vendor. | R-020 | 3 | 4 | 5 | 5 | 1 | 3 | 5 | 4 | 2 | 12 | 12 | High | Vendor Risk Assessment | 6 | Medium | Mitigate | Open | Annual vendor security audit and continuous monitoring. | 2026-12-31 | Third Party Risk Manager
R-021 | Cloud Security Management | Cloud Resource Provisioning | AWS / Azure Environment | Cloud Infrastructure Team | Cloud Security | Data Breach | Public Storage Bucket Configuration | Critical | Cloud Security Misconfiguration | Sensitive customer and banking data may be exposed due to improperly configured cloud resources such as public storage buckets or databases. | R-021 | 4 | 5 | 5 | 5 | 1 | 4 | 5 | 4 | 3 | 20 | 20 | Critical | Cloud Security Policy, Access Control Standards | 10 | High | Mitigate | Open | Deploy CSPM, perform cloud configuration reviews, enforce least privilege. | 2026-12-31 | Cloud Architect
R-022 | AI Governance | AI Usage Monitoring | AI Services and Customer Data | Information Security Team | Emerging Technology / AI | Data Leakage | Employees Using Public AI Models | High | AI Model Data Exposure | Employees may unintentionally expose sensitive customer information while using public AI tools. | R-022 | 4 | 4 | 5 | 5 | 1 | 3 | 5 | 3 | 2 | 16 | 16 | High | Acceptable Use Policy | 8 | Medium | Mitigate | Open | Implement AI governance policy, DLP controls and employee awareness. | 2026-12-31 | CISO
R-023 | Physical Security Management | Data Center Access Control | Data Center Infrastructure | Facilities Security Team | Physical Security | Unauthorized Physical Access | Weak Access Control Mechanisms | Critical | Physical Security Breach – Data Center | Unauthorized individuals may gain physical access to critical banking infrastructure, resulting in theft, sabotage or service disruption. | R-023 | 4 | 5 | 4 | 5 | 2 | 5 | 5 | 5 | 5 | 20 | 20 | Critical | CCTV, Access Cards, Security Guards | 8 | Medium | Mitigate | Open | Implement biometric access, visitor management and periodic physical audits. | 2026-10-31 | Facilities Security Manager
R-024 | ATM Security Management | ATM Fraud Prevention | ATM Network | Cards & Payments Team | Physical Security / Fraud | Card Data Theft | Lack of Anti-Skimming Controls | High | ATM Skimming Attack | Criminals may install skimming devices on ATMs to capture card information and PINs. | R-024 | 3 | 4 | 3 | 4 | 1 | 3 | 5 | 3 | 1 | 12 | 12 | High | ATM Monitoring and Inspections | 6 | Medium | Mitigate | Open | Install anti-skimming devices and increase ATM inspections. | 2026-11-30 | Cards & Payments Manager
R-025 | Application Security Management | API Security Monitoring | Open Banking APIs | Application Security Team | Application Security | API Abuse / Injection | No API Gateway and Rate Limiting | Critical | API Security Breach | Attackers may exploit insecure APIs to gain unauthorized access to customer data and banking services. | R-025 | 4 | 5 | 5 | 5 | 1 | 4 | 5 | 5 | 3 | 20 | 20 | Critical | API Authentication and Secure Coding Practices | 10 | High | Mitigate | Open | Deploy API Gateway, WAF, API monitoring and rate limiting controls. | 2026-12-31 | API Security Lead
R-026 | Secure Software Development Lifecycle | Third-Party Dependency Management | Banking Applications | DevSecOps Team | Third Party Risk / Cybersecurity | Malicious Code Injection | No Software Composition Analysis (SCA) | High | Software Supply Chain Attack | Malicious code may be introduced into banking applications through compromised open-source libraries or third-party software components. | R-026 | 4 | 4 | 4 | 5 | 1 | 4 | 5 | 5 | 4 | 16 | 16 | Critical | Manual Code Reviews | 8 | Medium | Mitigate | Open | Deploy SCA tools, vendor security validation, dependency scanning. | 2026-12-31 | DevSecOps Lead
R-027 | Mobile Application Security | Secure Mobile Development | Mobile Banking Application | Mobile Security Team | Application Security | Reverse Engineering | Lack of Code Obfuscation | High | Mobile Banking Application Vulnerability | Attackers may reverse engineer the banking application to extract secrets, API keys, or bypass security controls. | R-027 | 4 | 4 | 4 | 5 | 1 | 3 | 5 | 4 | 2 | 16 | 16 | High | Secure Coding Guidelines | 8 | Medium | Mitigate | Open | Implement code obfuscation, root detection, anti-tampering controls. | 2026-12-31 | Mobile Security Lead
R-028 | Security Awareness Management | Social Engineering Defense | Employees and Internal Systems | Security Awareness Team | Human Risk | Voice-Based Social Engineering | No Verification Procedure for Phone Requests | High | Vishing Attack | Attackers may impersonate IT support, management, or trusted parties to obtain credentials or sensitive information. | R-028 | 4 | 3 | 3 | 4 | 1 | 4 | 4 | 3 | 3 | 12 | 12 | High | Security Awareness Training | 6 | Medium | Mitigate | Open | Implement call verification procedures and regular vishing simulations. | 2026-10-31 | Security Awareness Lead
R-029 | Data Governance | Data Residency Compliance | Customer Data Repository | Compliance Team | Compliance / Legal | Cross-Border Data Transfer | Incorrect Cloud Region Selection | Critical | Data Residency Violation | Banking or customer data may be stored outside Egypt in violation of applicable laws and regulations. | R-029 | 4 | 5 | 5 | 5 | 1 | 4 | 5 | 4 | 2 | 20 | 20 | Critical | Data Classification and Hosting Policies | 8 | Medium | Mitigate | Open | Continuous data residency monitoring and cloud region validation. | 2026-09-30 | Compliance Manager
R-030 | Identity and Access Management | Authentication Security | Internet Banking Platform | IAM Team | Cybersecurity | Credential Stuffing | Password Reuse and Weak Authentication Controls | High | Credential Stuffing Attack | Attackers may use leaked credentials from other services to gain unauthorized access to customer accounts. | R-030 | 4 | 4 | 3 | 4 | 1 | 3 | 5 | 4 | 2 | 12 | 12 | High | Password Policy | 6 | Medium | Mitigate | Open | Enforce MFA, password blacklist, account lockout, and rate limiting. | 2026-10-31 | IAM Manager
R-031 | Incident Management | Regulatory Breach Notification | Personal Data Processing Systems | Compliance & Privacy Team | Compliance / Legal | Regulatory Sanctions | No Automated Breach Reporting Process | Critical | Failure to Report PDPL Breach within 72 Hours | Failure to notify the Personal Data Protection Center within the required timeframe may result in penalties and legal action. | R-031 | 4 | 5 | 5 | 4 | 1 | 3 | 4 | 3 | 2 | 20 | 20 | Critical | Incident Response Plan | 8 | Medium | Mitigate | Open | Implement automated breach notification workflow and escalation procedures. | 2026-09-30 | DPO
R-032 | Data Governance | Cross-Border Data Transfer | Customer Data Platforms | Compliance Team | Compliance / Legal | Regulatory Penalties | Uncontrolled International Data Transfer | Critical | Cross-Border Data Transfer Without PDPC License | Personal data may be transferred outside Egypt without required regulatory approval. | R-032 | 4 | 5 | 5 | 5 | 1 | 3 | 5 | 4 | 2 | 20 | 20 | Critical | Cloud Provider Review Process | 8 | Medium | Mitigate | Open | Implement data residency monitoring and transfer approval workflows. | 2026-10-31 | DPO / CISO
R-033 | Information Security Management | Regulatory Compliance | Enterprise Security Program | Information Security Team | Compliance / Cybersecurity | Regulatory Non-Compliance | Incomplete Security Controls | High | Failure to Meet NIS2 Equivalent Security Baseline | Security controls may not meet international cybersecurity requirements, resulting in compliance gaps. | R-033 | 3 | 3 | 5 | 4 | 1 | 4 | 4 | 4 | 4 | 12 | 12 | High | ISO 27001 Controls | 6 | Medium | Mitigate | Open | Conduct NIS2 gap assessment and formal compliance program. | 2026-12-31 | CISO
R-034 | Third Party Risk Management | Cloud Provider Management | Cloud Infrastructure | IT Operations | Operational / Third Party | Service Disruption | Single Cloud Provider Dependency | High | ICT Supply Chain Dependency | Excessive reliance on a single cloud provider may cause significant operational disruption if the provider becomes unavailable. | R-034 | 4 | 4 | 3 | 4 | 1 | 5 | 2 | 3 | 5 | 16 | 16 | High | Vendor SLA | 8 | Medium | Mitigate | Open | Develop multi-cloud strategy and alternative vendor plans. | 2026-12-31 | CTO
R-035 | Business Continuity Management | Resilience Testing | Critical Banking Services | Business Continuity Team | Operational / BCP | Service Outage | Inadequate Testing Program | High | Failure to Conduct Digital Operational Resilience Testing | Critical systems may fail during major incidents due to insufficient resilience testing. | R-035 | 4 | 4 | 3 | 4 | 1 | 5 | 2 | 3 | 5 | 16 | 16 | High | Annual BCP Testing | 8 | Medium | Mitigate | Open | Implement quarterly resilience exercises and threat-led testing. | 2026-12-31 | BCP Manager
R-036 | Security Awareness Management | Social Engineering Defense | Employees and Communication Channels | SOC Team / Security Awareness Team | Human Risk / Emerging Technology | AI-Generated Voice or Video Impersonation | No Verification Procedure for High-Risk Requests | Critical | Deepfake-Based Social Engineering Attack | Attackers may use AI-generated voice or video impersonation of executives to trick employees into transferring funds or disclosing sensitive information. | R-036 | 4 | 5 | 3 | 5 | 1 | 4 | 4 | 4 | 2 | 20 | 20 | Critical | Security Awareness Training | 10 | High | Mitigate | Open | Implement callback verification procedures and deepfake awareness training. | 2026-12-31 | SOC Manager
R-037 | Mobile Security Management | Mobile Threat Protection | Mobile Banking Application | Mobile Security Team | Application Security / Mobile | Banking Malware | Lack of Runtime Application Protection | High | Mobile Banking Trojan Infection | Malware installed on customer devices may intercept banking credentials and OTP codes. | R-037 | 4 | 4 | 3 | 5 | 1 | 3 | 5 | 4 | 2 | 16 | 16 | High | Certificate Pinning | 8 | Medium | Mitigate | Open | Implement RASP, anti-tampering, and root/jailbreak detection. | 2026-12-31 | Mobile Security Lead
R-038 | Privacy Governance | Data Protection Compliance | Privacy Management Program | Compliance Department | Compliance / Legal | Regulatory Penalties | No Formal DPO Registration | High | DPO Not Formally Appointed or Registered | Failure to appoint and register a Data Protection Officer may result in non-compliance with privacy regulations. | R-038 | 3 | 3 | 5 | 3 | 1 | 3 | 2 | 2 | 1 | 12 | 12 | High | Informal Privacy Responsibilities | 6 | Medium | Mitigate | Open | Appoint and register DPO and establish governance procedures. | 2026-10-31 | Compliance Manager
R-039 | Data Governance | Data Inventory Management | Personal Data Repositories | Data Governance Team | Compliance | Regulatory Inspection Failure | No Centralized Data Processing Inventory | High | Lack of Records of Processing Activities (ROPA) | The organization may fail to demonstrate compliance due to missing records of personal data processing activities. | R-039 | 3 | 3 | 5 | 3 | 1 | 3 | 3 | 3 | 1 | 12 | 12 | High | Informal Data Documentation | 6 | Medium | Mitigate | Open | Implement automated data discovery and maintain ROPA records within GRC platform. | 2026-12-31 | Data Governance Lead
R-040 | Identity and Access Management | Customer Authentication | Digital Banking Platform | IAM Team / Fraud Team | Cybersecurity / Fraud | SIM Swap Fraud | Reliance on SMS OTP as Sole Authentication Factor | Critical | Account Takeover via SIM Swap Attack | Attackers may gain control of customer accounts by hijacking phone numbers used for SMS-based authentication. | R-040 | 4 | 5 | 4 | 5 | 1 | 4 | 5 | 5 | 3 | 20 | 20 | Critical | SMS OTP Authentication | 10 | High | Mitigate | Open | Implement authenticator-based MFA, biometric authentication and SIM swap detection controls. | 2026-12-31 | Fraud Manager
R-041 | Privacy Risk Management | DPIA Management | Personal Data Processing Activities | Privacy & Compliance Team | Compliance / Legal | Regulatory Non-Compliance | No Formal DPIA Process | High | Failure to Submit DPIA for High-Risk Processing | High-risk personal data processing activities may be implemented without conducting a Data Protection Impact Assessment, resulting in regulatory violations. | R-041 | 3 | 3 | 5 | 3 | 1 | 3 | 3 | 3 | 1 | 12 | 12 | High | Informal Review Process | 6 | Medium | Mitigate | Open | Formalize DPIA process and integrate with project lifecycle. | 2026-12-31 | DPO
R-042 | Network Security Management | Network Segmentation | Internal Banking Network | Network Security Team | Cybersecurity | Lateral Movement | Flat Network Architecture | Critical | Insufficient Network Segmentation | Attackers may move laterally across the network after an initial compromise due to insufficient segmentation between critical systems. | R-042 | 4 | 5 | 4 | 5 | 1 | 5 | 5 | 5 | 4 | 20 | 20 | Critical | Firewall Rules | 10 | High | Mitigate | Open | Implement micro-segmentation and zero-trust network architecture. | 2026-12-31 | Network Security Manager
R-043 | Incident Management | Regulatory Incident Reporting | SIEM / Incident Management Platform | SOC Team / Compliance Team | Compliance / Cybersecurity | Regulatory Breach | Manual Incident Escalation Process | High | ICT Incident Reporting Delay | Critical cybersecurity incidents may not be reported within regulatory timelines due to inefficient reporting processes. | R-043 | 4 | 4 | 5 | 4 | 1 | 4 | 2 | 3 | 3 | 16 | 16 | High | Incident Response Procedure | 8 | Medium | Mitigate | Open | Automate incident notification and reporting workflows. | 2026-11-30 | SOC Manager
R-044 | Third Party Risk Management | Vendor Security Assessment | External Suppliers and Service Providers | Vendor Risk Management Team | Third Party Risk | Supply Chain Compromise | No Formal Vendor Security Assessment Program | High | Supply Chain Security Assessment Failure | Critical vendors may introduce cybersecurity risks due to insufficient security assessments and monitoring. | R-044 | 3 | 4 | 4 | 4 | 1 | 4 | 4 | 4 | 4 | 12 | 12 | High | Basic Vendor Contracts | 6 | Medium | Mitigate | Open | Establish vendor security assessment framework and periodic audits. | 2026-12-31 | Vendor Risk Manager
R-045 | Security Monitoring | User Activity Monitoring | Internal Banking Systems | Security Operations Center | Human Risk / Security Monitoring | Insider Threat | Lack of User Behavior Analytics (UEBA) | High | Insider Threat Detection Failure | Malicious or negligent employees may access or exfiltrate sensitive information without detection. | R-045 | 3 | 4 | 4 | 5 | 1 | 4 | 5 | 4 | 2 | 12 | 12 | High | Access Reviews and Logging | 6 | Medium | Mitigate | Open | Deploy UEBA and DLP solutions with continuous monitoring. | 2026-12-31 | SOC Manager
R-046 | Compliance Management | Control Mapping | Wadjet GRC Platform | Compliance Team | Compliance | Incorrect Compliance Assessment | Incorrect Framework Mapping | Critical | Compliance Mapping Failure | Incorrect mapping between regulations and controls may lead to inaccurate compliance reports and audit findings. | R-046 | 4 | 4 | 5 | 4 | 1 | 4 | 1 | 5 | 2 | 16 | 16 | High | Peer Review Process | 8 | Medium | Mitigate | Open | Automated mapping validation and periodic compliance reviews. | 2026-12-31 | Compliance Manager
R-047 | Compliance Automation | Evidence Collection | n8n Workflows / Integrations | Automation Team | Operational | Missing Audit Evidence | Workflow Failure or Integration Failure | High | Automated Evidence Collection Failure | Automated evidence collection processes may fail, resulting in incomplete audit evidence and compliance gaps. | R-047 | 3 | 3 | 5 | 3 | 1 | 4 | 1 | 4 | 4 | 12 | 12 | High | Workflow Monitoring Dashboard | 6 | Medium | Mitigate | Open | Implement workflow health monitoring, alerting, and failover mechanisms. | 2026-11-30 | Automation Lead
R-048 | Risk Management | Risk Scoring & Reporting | Risk Dashboard | Enterprise Risk Team | Risk Management | Incorrect Executive Decision Making | Incorrect Risk Scoring Logic | High | Risk Heatmap Inaccuracy | Risk calculations may be inaccurate due to incorrect formulas or scoring logic, leading to poor management decisions. | R-048 | 3 | 4 | 3 | 3 | 1 | 4 | 1 | 5 | 2 | 12 | 12 | High | Manual Validation Reviews | 6 | Medium | Mitigate | Open | Implement automated validation checks and independent risk model reviews. | 2026-12-31 | Risk Manager

## Mitigation Plan
WADJET GRC — MITIGATION PLAN ¦ 48 Risks ¦ Total Budget: $4,275,000 ¦ Est. Loss Prevented: $109,000,000
Risk ID | Risk Title | Category | Inherent Risk | Residual Risk (Exhausted) | Residual Risk (Recommended) | Risk Appetite | Budget | Mitigation Actions | Owner | Target Date | Status | RAG | Dependencies | Issues / Blockers | Risk Source | Review Freq | Last Review
📋 COMPLIANCE & LEGAL RISKS
R-004 | Regulatory Non-Compliance | Compliance | High | High | Medium | Zero | $95K | • Deploy continuous compliance monitoring against CBE Framework • Generate automated gap analysis reports monthly • Conduct quarterly compliance review with CISO • Provide compliance dashboard for executive management | Compliance Manager | 2026-10-31 | In Progress | ● | GRC platform deployment | Data migration from legacy systems | Audit | Quarterly | 2026-06-01
R-013 | Improper Data Retention Management | Compliance | High | High | Medium | Zero | $30K | • Document retention period requirements for each data type • Configure automated deletion after retention period expires • Conduct annual retention policy review with legal • Implement legal hold process for litigation cases | Compliance Manager | 2026-10-31 | Not Started | ● | Legal department review | None | Audit | Quarterly | 2026-06-01
R-029 | Data Residency Violation | Compliance | Critical | Critical | High | Zero | $60K | • Implement continuous cloud region monitoring for all data • Configure automated blocking of cross-border data transfers • Deploy real-time alerts for data residency violations • Conduct quarterly cloud configuration audit | Compliance Manager | 2026-09-30 | In Progress | ● | CSPM tool deployment | Cloud provider configuration | Regulatory | Monthly | 2026-06-01
R-031 | 72-Hour PDPL Breach Notification Failure | Compliance | Critical | Critical | High | Zero | $75K | • Deploy automated breach detection system • Configure notification workflow to PDPC • Deploy 72-hour countdown timer dashboard • Automate legal team notification upon breach detection | DPO | 2026-09-30 | Not Started | ● | Incident response automation | Legal process definition | Regulatory | Quarterly | 2026-06-01
R-032 | Cross-Border Data Transfer Without License | Compliance | Critical | Critical | Critical | Zero | $25K | • Implement data residency monitoring for all transfers • Configure approval workflow for international data transfers • Deploy automated blocking of unauthorized transfers • Submit PDPC licence application within 30 days | DPO / CISO | 2026-10-31 | Not Started | ● | PDPC licence application | Regulatory process is slow | Regulatory | Monthly | 2026-06-01
R-033 | Failure to Meet NIS2 Security Baseline | Compliance | High | High | Low | Zero | $120K | • Conduct comprehensive NIS2 gap assessment • Implement all missing controls identified • Conduct annual compliance review against NIS2 • Provide management reporting on NIS2 readiness | CISO | 2026-12-31 | Not Started | ● | External consultant engagement | Consultant procurement in progress | Assessment | Quarterly | 2026-06-01
R-038 | DPO Not Formally Appointed or Registered | Compliance | High | High | High | Zero | $10K | • Issue formal DPO appointment letter with signatures • Register DPO with PDPC within 30 days • Document DPO roles and responsibilities • Publish DPO contact information internally | Compliance Manager | 2026-10-31 | In Progress | ● | HR approval for appointment | None | Regulatory | Quarterly | 2026-06-01
R-039 | Lack of Records of Processing Activities | Compliance | High | High | Medium | Zero | $50K | • Deploy automated data discovery tool • Create and maintain ROPA in GRC platform • Update ROPA quarterly or after any material change • Conduct data mapping for all processing activities | Data Governance Lead | 2026-12-31 | Not Started | ● | Data discovery tool procurement | None | Audit | Quarterly | 2026-06-01
R-041 | Failure to Submit DPIA for High-Risk Processing | Compliance | High | High | High | Zero | $20K | • Document formal DPIA process and procedure • Conduct DPIA for all high-risk projects before launch • Ensure DPO reviews and approves all DPIAs • Maintain DPIA register with regular review schedule | DPO | 2026-12-31 | Not Started | ● | Project management integration | None | Assessment | Quarterly | 2026-06-01
R-043 | ICT Incident Reporting Delay | Compliance | High | High | Medium | Low | $45K | • Automate incident notification and reporting workflows • Integrate SIEM with regulatory reporting system • Deploy real-time escalation dashboard for SOC • Conduct quarterly regulatory reporting drill | SOC Manager | 2026-11-30 | Not Started | ● | SIEM integration project | Integration complexity | Regulatory | Monthly | 2026-06-01
🛡️ CYBERSECURITY RISKS
R-001 | Credential Theft Through Phishing | Cybersecurity | Critical | Critical | Low | Low | $45K | • Enforce MFA for all users (prioritise privileged accounts) • Conduct quarterly phishing simulations • Deploy advanced email gateway with malicious link detection • Monthly security awareness training for all employees | SOC Manager | 2026-12-31 | In Progress | ● | MFA licence procurement | Budget approval pending | Incident | Quarterly | 2026-06-01
R-002 | Ransomware Attack | Cybersecurity | Critical | Critical | Low | Very Low | $250K | • Deploy EDR on all endpoints with 24/7 monitoring • Weekly vulnerability patching for critical systems • Daily backups with monthly restoration testing • Application whitelisting for critical systems | SOC Manager | 2026-12-31 | In Progress | ● | EDR tool procurement | Vendor selection ongoing | Assessment | Monthly | 2026-06-01
R-009 | Unpatched Critical Vulnerability | Cybersecurity | High | High | Medium | Very Low | $80K | • Weekly vulnerability scanning using automated tools • 48-hour SLA for patching critical vulnerabilities • Automated patch deployment for non-critical systems • Monthly patch governance review with IT leadership | Vulnerability Lead | 2026-10-31 | Not Started | ● | Vulnerability scanner licence | Budget approval required | Scan | Weekly | 2026-06-01
R-012 | Failure to Detect Security Incidents | Cybersecurity | High | High | Medium | Low | $180K | • Implement centralised logging for all systems • Deploy 24/7 SOC coverage with shift rotation • Conduct monthly SIEM alert tuning • Deploy UEBA for insider threat detection | SOC Manager | 2026-11-30 | Not Started | ● | SIEM platform upgrade | Vendor contract renewal pending | Audit | Quarterly | 2026-06-01
R-018 | Delayed Vulnerability Remediation | Cybersecurity | High | High | High | Low | $40K | • Deploy remediation SLA dashboard with real-time updates • Configure automated alerts when SLA is breached • Conduct weekly remediation review with IT leads • Implement escalation process for overdue patches | Vulnerability Lead | 2026-10-31 | In Progress | ● | Dashboard development | Resource constraints | Assessment | Monthly | 2026-06-01
R-030 | Credential Stuffing Attack | Cybersecurity | High | High | Medium | Low | $35K | • Implement rate limiting on all login APIs • Deploy password blacklist to prevent weak passwords • Enforce MFA for all customer accounts • Configure account lockout after 5 failed attempts | IAM Manager | 2026-10-31 | Not Started | ● | IAM platform upgrade | No major blockers | Incident | Quarterly | 2026-06-01
R-040 | Account Takeover via SIM Swap Attack | Cybersecurity | Critical | Critical | High | Very Low | $120K | • Implement authenticator-based MFA (replace SMS OTP) • Deploy biometric authentication for high-value transactions • Implement SIM swap detection controls • Configure alerts for suspicious account changes | Fraud Manager | 2026-12-31 | Not Started | ● | MFA platform upgrade | Carrier coordination required | Incident | Monthly | 2026-06-01
R-042 | Insufficient Network Segmentation | Cybersecurity | Critical | Critical | High | Very Low | $350K | • Implement micro-segmentation for all critical systems • Deploy zero-trust network architecture • Conduct quarterly firewall rules review • Perform annual network segmentation penetration testing | Network Security Manager | 2026-12-31 | Not Started | ● | Network hardware upgrade | Budget approval required | Audit | Quarterly | 2026-06-01
🔐 INFORMATION SECURITY RISKS
R-003 | Unauthorized Privileged Access | Info Security | High | High | Low | Very Low | $150K | • Deploy PAM solution for all privileged accounts • Conduct quarterly privileged access review • Reduce privileged accounts by 80% • Implement just-in-time privileged access | IAM Manager | 2026-11-30 | In Progress | ● | PAM solution deployment | Active Directory integration | Assessment | Quarterly | 2026-06-01
R-005 | Customer Data Leakage | Info Security | High | High | Low | Zero | $200K | • Deploy full DLP for data-at-rest and data-in-motion • Encrypt all sensitive customer data at rest and in transit • Conduct monthly access permission review • Implement data classification for all databases | DPO | 2026-12-31 | Not Started | ● | DLP tool procurement | Budget approval required | Incident | Monthly | 2026-06-01
R-008 | Insider Threat Activity | Info Security | High | High | Medium | Low | $120K | • Deploy UEBA solution for user behaviour monitoring • Log all user activities with tamper-proof audit trail • Conduct quarterly employee access review • Automate employee offboarding process | InfoSec Manager | 2026-12-31 | Not Started | ● | UEBA tool procurement | Vendor selection in progress | Incident | Quarterly | 2026-06-01
R-011 | MFA Not Enforced | Info Security | High | High | High | Zero | $40K | • Enforce MFA for all users (100% coverage) • Prioritise privileged accounts and remote access • Use authenticator app (TOTP) — avoid SMS OTP • Eliminate password-only authentication within 6 months | IAM Manager | 2026-12-31 | In Progress | ● | MFA licence procurement | User communication pending | Audit | Quarterly | 2026-06-01
R-016 | Database Security Misconfiguration | Info Security | High | High | Medium | Zero | $35K | • Conduct quarterly database configuration review • Deploy automated configuration scanning tool • Remove all default accounts from databases • Implement and enforce database hardening standards | Database Manager | 2026-12-31 | Not Started | ● | Scanning tool deployment | None | Scan | Monthly | 2026-06-01
R-017 | Misuse of Privileged Accounts | Info Security | High | High | Medium | Very Low | $120K | • Deploy PAM solution for all privileged accounts • Log all admin commands with detailed audit trail • Enable session recording for critical system access • Document and test break-glass procedure annually | IAM Manager | 2026-12-31 | Not Started | ● | PAM tool deployment | Same as R-003 | Incident | Quarterly | 2026-06-01
⚙️ OPERATIONAL & BCP RISKS
R-007 | Backup and Recovery Failure | Operational | High | High | Low | Very Low | $80K | • Conduct quarterly backup restoration testing • Implement 3-2-1 backup rule (3 copies, 2 media, 1 offsite) • Configure daily backup success monitoring with alerts • Conduct annual disaster recovery drill | IT Operations Manager | 2026-11-30 | Not Started | ● | Backup infrastructure upgrade | Budget approval required | Test | Monthly | 2026-06-01
R-010 | Incident Response Failure | Operational | High | High | Medium | Low | $40K | • Conduct quarterly tabletop exercises with SOC team • Update Incident Response Plan annually • Conduct post-incident review for all major incidents • Maintain 24/7 SOC coverage with escalation procedures | SOC Manager | 2026-12-31 | In Progress | ● | Exercise scenario development | None | Exercise | Quarterly | 2026-06-01
R-014 | Business Continuity Failure | Operational | High | High | Medium | Zero | $300K | • Conduct annual DR testing with full failover • Perform Business Impact Analysis every 2 years • Provide BCP training for all employees annually • Maintain crisis communication plan with regular updates | BCP Manager | 2026-12-31 | Not Started | ● | DR site construction | Facility construction in progress | Test | Quarterly | 2026-06-01
R-015 | Unauthorized System Changes | Operational | Medium | Medium | Low | Medium | $25K | • Enforce change approval workflow for all changes • Require peer review for all changes • Maintain change logging with audit trail • Document emergency change procedure with post-review | Change Manager | 2026-09-30 | In Progress | ● | ITSM tool upgrade | None | Audit | Monthly | 2026-06-01
R-035 | Digital Resilience Testing Failure | Operational | High | High | High | Low | $150K | • Conduct quarterly resilience exercises • Perform threat-led penetration testing (TLPT) annually • Implement post-exercise improvement plan tracking • Deploy resilience metrics dashboard | BCP Manager | 2026-12-31 | Not Started | ● | External testing provider | Procurement in progress | Assessment | Quarterly | 2026-06-01
R-047 | Automated Evidence Collection Failure | Operational | High | High | High | Very Low | $30K | • Configure workflow health check every 5 minutes • Implement retry logic with 3 attempts before failure • Deploy real-time alert on workflow failure • Document and test manual fallback procedure quarterly | Automation Lead | 2026-11-30 | In Progress | ● | Monitoring dashboard deployment | None | Assessment | Monthly | 2026-06-01
👥 HUMAN RISK
R-019 | Insufficient Security Awareness | Human Risk | High | High | Medium | Low | $25K | • Deliver weekly security tips to all employees • Conduct quarterly phishing simulations • Reward employees who report phishing attempts • Deliver mandatory annual security training for all | Security Awareness Lead | 2026-12-31 | In Progress | ● | Training platform | None | Assessment | Quarterly | 2026-06-01
R-028 | Vishing Attack | Human Risk | High | High | High | Low | $15K | • Implement call verification procedures for all requests • Train employees on phone scam detection • Conduct quarterly vishing simulations • Establish process to report suspicious calls | Security Awareness Lead | 2026-10-31 | Not Started | ● | Simulation platform | None | Incident | Quarterly | 2026-06-01
R-036 | Deepfake-Based Social Engineering Attack | Human Risk | Critical | Critical | Critical | Very Low | $100K | • Implement out-of-band verification for all financial requests • Conduct deepfake awareness training for all employees • Establish policy: no financial requests by voice only • Deploy deepfake detection tools for critical communications | SOC Manager | 2026-12-31 | Not Started | ● | Detection tool evaluation | Emerging technology | Incident | Monthly | 2026-06-01
R-045 | Insider Threat Detection Failure | Human Risk | High | High | Medium | Low | $120K | • Deploy UEBA solution for user behaviour monitoring • Configure DLP to prevent data exfiltration • Automate employee offboarding process • Conduct quarterly insider threat awareness training | SOC Manager | 2026-12-31 | Not Started | ● | UEBA tool deployment | Same as R-008 | Assessment | Quarterly | 2026-06-01
🤝 THIRD PARTY RISKS
R-006 | Third Party Security Breach | Third Party | High | High | Medium | Low | $60K | • Conduct pre-contract vendor security assessment for all vendors • Include security requirements in all vendor contracts • Conduct annual security review for critical vendors • Implement vendor risk rating system | Vendor Risk Manager | 2026-09-30 | In Progress | ● | Vendor assessment template | None | Vendor | Quarterly | 2026-06-01
R-020 | Third Party Data Exposure | Third Party | High | High | High | Zero | $30K | • Require encryption of bank data at all vendors • Include audit rights in all vendor contracts • Conduct quarterly vendor compliance review • Execute Data Processing Agreement with all vendors | Third Party Risk Manager | 2026-12-31 | Not Started | ● | Legal department review | None | Vendor | Quarterly | 2026-06-01
R-026 | Software Supply Chain Attack | Third Party | High | High | High | Low | $70K | • Deploy SCA tools in CI/CD pipeline • Scan all open-source libraries before use • Conduct quarterly dependency updates • Require SBOM from all software vendors | DevSecOps Lead | 2026-12-31 | Not Started | ● | SCA tool procurement | Tool evaluation in progress | Assessment | Monthly | 2026-06-01
R-034 | ICT Supply Chain Dependency | Third Party | High | High | High | Medium | $200K | • Develop and execute multi-cloud strategy • Create exit plan for each critical vendor • Conduct annual vendor switch testing • Implement vendor concentration monitoring dashboard | CTO | 2026-12-31 | Not Started | ● | Cloud architecture redesign | Strategic decision pending | Assessment | Quarterly | 2026-06-01
R-044 | Supply Chain Security Assessment Failure | Third Party | High | High | High | Low | $50K | • Establish formal vendor security assessment framework • Classify vendors by criticality level • Conduct quarterly audits for critical vendors • Implement vendor security scorecard program | Vendor Risk Manager | 2026-12-31 | Not Started | ● | Assessment framework development | None | Audit | Quarterly | 2026-06-01
📱 APPLICATION & MOBILE SECURITY
R-025 | API Security Breach | App Security | Critical | Critical | High | Very Low | $150K | • Deploy API Gateway for all external APIs • Implement rate limiting and throttling • Deploy WAF for all public APIs • Implement strong authentication and authorization | API Security Lead | 2026-12-31 | Not Started | ● | API Gateway deployment | Infrastructure setup in progress | Assessment | Quarterly | 2026-06-01
R-027 | Mobile Banking App Vulnerability | App Security | High | High | Medium | Low | $80K | • Implement code obfuscation for mobile app • Deploy root/jailbreak detection • Implement anti-tampering controls • Deploy RASP for mobile application | Mobile Security Lead | 2026-12-31 | In Progress | ● | Mobile app update | None | Scan | Monthly | 2026-06-01
R-037 | Mobile Banking Trojan Infection | App Security | High | High | Medium | Low | $60K | • Deploy RASP for mobile app • Implement certificate pinning for all connections • Deploy malware detection on customer devices • Configure alerts to customers about detected malware | Mobile Security Lead | 2026-12-31 | Not Started | ● | RASP integration | None | Incident | Quarterly | 2026-06-01
☁️ CLOUD, PHYSICAL & AI RISKS
R-021 | Cloud Security Misconfiguration | Cloud | Critical | Critical | High | Very Low | $100K | • Deploy CSPM tool for continuous cloud monitoring • Implement Infrastructure as Code with security scanning • Conduct monthly cloud configuration review • Enforce least privilege for all cloud resources | Cloud Architect | 2026-12-31 | Not Started | ● | CSPM tool procurement | Tool evaluation in progress | Scan | Monthly | 2026-06-01
R-022 | AI Model Data Exposure | Emerging Tech | High | High | High | Low | $50K | • Issue and enforce AI acceptable use policy • Configure DLP for data sent to AI tools • Conduct employee training on AI risks • Deploy internal AI tools for sensitive data | CISO | 2026-12-31 | Not Started | ● | Policy approval | None | Assessment | Quarterly | 2026-06-01
R-023 | Physical Security Breach – Data Center | Physical | Critical | Critical | Low | Very Low | $200K | • Deploy biometric access control for data centre • Implement visitor management system • Maintain 24/7 CCTV monitoring with retention • Conduct quarterly physical security audit | Facilities Security Manager | 2026-10-31 | In Progress | ● | Access system upgrade | Vendor installation in progress | Audit | Quarterly | 2026-06-01
R-024 | ATM Skimming Attack | Physical | High | High | Low | Low | $150K | • Install anti-skimming devices on all ATMs • Conduct weekly ATM physical inspections • Provide customer skimming awareness materials • Deploy transaction monitoring for anomaly detection | Cards & Payments Manager | 2026-11-30 | Not Started | ● | Device procurement | None | Incident | Monthly | 2026-06-01
📊 RISK MANAGEMENT & GRC
R-046 | Compliance Mapping Failure | Risk Mgmt | High | High | Medium | Zero | $40K | • Implement automated mapping validation in GRC platform • Engage external GRC consultant for review • Maintain version control for all frameworks • Configure automated testing for mappings | Compliance Manager | 2026-12-31 | In Progress | ● | External consultant engagement | None | Assessment | Quarterly | 2026-06-01
R-048 | Risk Heatmap Inaccuracy | Risk Mgmt | High | High | Low | Zero | $20K | • Implement unit tests for all risk score formulas • Deploy validation dashboard for engineers • Conduct quarterly risk model review • Maintain audit log for all risk calculation changes | Risk Manager | 2026-12-31 | In Progress | ● | Testing framework | None | Assessment | Quarterly | 2026-06-01

## Budget Assumptions
WADJET GRC — BUDGET ASSUMPTIONS SHEET ¦ Detailed Cost Justification per Risk
All estimates are based on market benchmarks for Egyptian banking sector / mid-size financial institutions. Costs in USD. Blue figures are hardcoded assumptions.
Risk ID | Category | Budget Item / Description | Estimated Cost ($) | Justification / Source | Sub-Total ($)
R-042 | Network Segmentation | Micro-segmentation software + implementation | 150000 | Market rate for Cisco/Palo Alto micro-segmentation for mid-size bank (30–50 servers)
R-042 | Network Segmentation | Zero-trust architecture deployment (Zscaler / Cloudflare ZTNA) | 100000 | ZTNA licensing for 500–1,000 users
R-042 | Network Segmentation | Firewall rules review + annual penetration testing | 100000 | Quarterly external consultant fees + annual pen test
TOTAL — Network Segmentation |  |  | 350000
R-005 | Data Leakage Prevention | Full DLP deployment – Forcepoint / Symantec (1,000 endpoints + email DLP) | 100000 | Endpoint + email DLP licence bundle
R-005 | Data Leakage Prevention | Encryption for all sensitive data at rest & in transit (Vormetric / CipherTrust) | 50000 | Deployment & licensing
R-005 | Data Leakage Prevention | Data classification + access reviews (Varonis or manual effort) | 50000 | Tooling + internal effort estimate
TOTAL — Data Leakage Prevention |  |  | 200000
R-003 / R-017 | Privileged Access Management | PAM solution – CyberArk / Delinea (50–100 privileged accounts, licence + implementation) | 150000 | Industry benchmark for PAM deployment at similar institution size
TOTAL — Privileged Access Management |  |  | 150000
R-025 | API Security | API Gateway – Kong / AWS API Gateway / MuleSoft (annual licence) | 60000 | Annual gateway licensing
R-025 | API Security | WAF for APIs – Cloudflare / Imperva | 40000 | Annual WAF subscription
R-025 | API Security | Rate limiting + authentication implementation (2–3 months developer effort) | 50000 | Internal developer cost estimate
TOTAL — API Security |  |  | 150000
R-002 | Ransomware Protection | EDR solution – CrowdStrike / SentinelOne / Defender for Endpoint (1,000 endpoints × $100/yr) | 100000 | Per-endpoint annual licence
R-002 | Ransomware Protection | Backup infrastructure + DR cloud storage + annual restoration testing | 150000 | Cloud backup + quarterly DR test fees
TOTAL — Ransomware Protection |  |  | 250000
R-021 | Cloud Security | CSPM tool – Wiz / Orca / Prisma Cloud (annual subscription) | 40000 | Cloud-native CSPM for multi-cloud environment
R-021 | Cloud Security | IaC security scanning integration in CI/CD pipeline (Checkov / Bridgecrew) | 60000 | Tool licence + engineer integration effort
TOTAL — Cloud Security |  |  | 100000
R-023 | Physical Security – Data Center | Biometric access control system – hardware + installation | 100000 | Hardware procurement + vendor installation at primary data centre
R-023 | Physical Security – Data Center | Visitor management system + CCTV upgrade (software + cameras + cabling) | 100000 | VMS licence + camera hardware + installation
TOTAL — Physical Security – Data Center |  |  | 200000
R-014 | Business Continuity & DR | DR site construction / co-location setup | 200000 | Co-location fees + infrastructure buildout (12-month commitment)
R-014 | Business Continuity & DR | Annual DR failover testing + BIA consultancy | 100000 | External DR test vendor + BIA facilitation
TOTAL — Business Continuity & DR |  |  | 300000
R-012 | SOC & SIEM | SIEM platform upgrade – Splunk / Microsoft Sentinel (annual licence + professional services) | 120000 | Enterprise SIEM licence for ~500 log sources
R-012 | SOC & SIEM | 24/7 SOC coverage expansion + UEBA add-on module | 60000 | Additional analyst shifts + UEBA licence
TOTAL — SOC & SIEM |  |  | 180000
R-035 | Digital Resilience Testing | TLPT – threat-led penetration test (annual, external certified provider) | 100000 | TIBER-EU / CBEST-style test with certified provider
R-035 | Digital Resilience Testing | Quarterly resilience exercises + improvement tracking dashboard | 50000 | Facilitation cost + internal dashboard development
TOTAL — Digital Resilience Testing |  |  | 150000
R-001 / R-011 / R-030 | IAM & MFA | MFA platform licence – Okta / Duo Security (all users + privileged) | 45000 | Per-user annual licence for ~500 internal + 200 privileged users
R-001 / R-011 / R-030 | IAM & MFA | IAM platform upgrade for rate-limiting + lockout policies | 35000 | IAM platform upgrade effort
TOTAL — IAM & MFA |  |  | 80000
R-008 / R-045 | Insider Threat & UEBA | UEBA solution – Securonix / Exabeam (licence + implementation) | 120000 | Single deployment covering both R-008 and R-045
TOTAL — Insider Threat & UEBA |  |  | 120000
R-006 / R-044 | Third Party & Supply Chain | Vendor security assessment framework + scorecard tool | 50000 | Onshore GRC consultant + tooling
R-006 / R-044 | Third Party & Supply Chain | Annual critical-vendor audits (external) – top 10 vendors | 60000 | Audit fees for top-10 critical vendors
TOTAL — Third Party & Supply Chain |  |  | 110000
R-024 | ATM Physical Security | Anti-skimming devices – full ATM fleet (hardware procurement) | 100000 | Hardware cost per ATM × fleet size estimate
R-024 | ATM Physical Security | Transaction anomaly detection monitoring + alerts integration | 50000 | Integration with existing fraud monitoring platform
TOTAL — ATM Physical Security |  |  | 150000
R-033 | Compliance – NIS2 | External NIS2 gap assessment + remediation consultancy (8–12 weeks) | 120000 | Specialist GRC consultant
TOTAL — Compliance – NIS2 |  |  | 120000
R-042 / R-034 | Network & Cloud Architecture | Multi-cloud strategy + vendor exit plans + monitoring dashboard | 200000 | Strategic architecture redesign effort
TOTAL — Network & Cloud Architecture |  |  | 200000
R-022 | AI Risk | AI acceptable use policy + DLP configuration for AI tools | 30000 | Policy drafting (legal + GRC) + DLP rule development
R-022 | AI Risk | Employee AI risk awareness training (LMS module + content) | 20000 | LMS module + facilitation
TOTAL — AI Risk |  |  | 50000
R-036 | Human Risk – Deepfake | Deepfake detection tool evaluation + pilot deployment | 70000 | Vendor POC + licensing (emerging technology)
R-036 | Human Risk – Deepfake | Deepfake awareness training campaign | 30000 | Targeted awareness content + simulation exercises
TOTAL — Human Risk – Deepfake |  |  | 100000
R-040 | Fraud – SIM Swap | Authenticator-based MFA migration (replace SMS OTP) | 80000 | MFA platform upgrade + migration project
R-040 | Fraud – SIM Swap | SIM swap detection + carrier coordination | 40000 | Technical integration + carrier API fees
TOTAL — Fraud – SIM Swap |  |  | 120000
R-007 | Backup & Recovery | Backup infrastructure upgrade (hardware + cloud storage) | 60000 | On-prem + cloud backup hardware
R-007 | Backup & Recovery | Annual DR testing + monitoring tooling | 20000 | DR test vendor + monitoring licence
TOTAL — Backup & Recovery |  |  | 80000
R-026 | Software Supply Chain | SCA tools integration in CI/CD + SBOM requirements | 70000 | SCA licence + engineer integration effort
TOTAL — Software Supply Chain |  |  | 70000
R-009 | Vulnerability Management | Vulnerability scanner licence (Tenable / Qualys) | 55000 | Annual licence for enterprise vulnerability scanner
R-009 | Vulnerability Management | Automated patch management tooling | 25000 | Patch automation tool licence + setup
TOTAL — Vulnerability Management |  |  | 80000
R-027 / R-037 | Mobile Security | RASP deployment + certificate pinning for mobile app | 60000 | RASP integration + security hardening
R-027 / R-037 | Mobile Security | Code obfuscation + root/jailbreak detection implementation | 20000 | Development effort
TOTAL — Mobile Security |  |  | 80000
R-019 / R-028 | Security Awareness | Annual security training platform licence (KnowBe4 / Proofpoint) | 20000 | Per-user licence for awareness training platform
R-019 / R-028 | Security Awareness | Phishing + vishing simulation campaigns (quarterly) | 20000 | Campaign delivery + facilitation
TOTAL — Security Awareness |  |  | 40000
R-046 / R-048 | Risk Mgmt & GRC Tooling | GRC platform enhancements + compliance mapping validation | 40000 | Platform development + consultant engagement
R-046 / R-048 | Risk Mgmt & GRC Tooling | Risk model testing framework + validation dashboard | 20000 | Internal engineering effort
TOTAL — Risk Mgmt & GRC Tooling |  |  | 60000
R-010 | Incident Response | Tabletop exercise facilitation (quarterly) | 20000 | External facilitator fees
R-010 | Incident Response | IR plan update + post-incident review tooling | 20000 | Consultant + tooling
TOTAL — Incident Response |  |  | 40000
R-015 | Change Management | ITSM tool upgrade (ServiceNow / Jira) | 25000 | ITSM licence upgrade
TOTAL — Change Management |  |  | 25000
R-016 | Database Security | Database configuration scanning tool (DbProtect / Imperva) | 35000 | Annual licence + deployment
TOTAL — Database Security |  |  | 35000
R-020 | Third Party Data Exposure | DPA templates + legal review for all vendors | 30000 | Legal fees + template development
TOTAL — Third Party Data Exposure |  |  | 30000
R-031 | PDPL Breach Notification | Automated breach detection + PDPC notification workflow | 75000 | SIEM integration + notification system
TOTAL — PDPL Breach Notification |  |  | 75000
R-039 | Data Governance – ROPA | Automated data discovery tool + ROPA maintenance | 50000 | Tool licence + data mapping effort
TOTAL — Data Governance – ROPA |  |  | 50000
R-047 | Automation & Evidence | Workflow health check + retry logic + alerting dashboard | 30000 | Internal development + monitoring licence
TOTAL — Automation & Evidence |  |  | 30000
GRAND TOTAL — ALL RISK MITIGATION BUDGETS |  |  | 7550000
NOTES & ASSUMPTIONS
1. All costs are estimates based on publicly available market rates as of 2025–2026. Actual procurement may vary ±20%.
2. Costs denominated in USD. Convert to EGP at prevailing CBE exchange rate at time of procurement.
3. Blue figures in "Estimated Cost" column are hardcoded inputs — update when vendor quotes are received.
4. Shared tools (e.g., PAM for R-003/R-017; UEBA for R-008/R-045) are budgeted once to avoid double-counting.
5. Personnel / internal effort costs are included where a tool implementation requires significant engineering time.
6. This sheet should be reviewed quarterly and updated after each procurement or vendor negotiation.

## Risk Methodology Ref
RISK SCORING METHODOLOGY — REFERENCE CARD
LIKELIHOOD SCALE
Score | Level | Description
1 | Very Unlikely | Rarely occurs
2 | Unlikely | May occur once in 5+ years
3 | Possible | May occur once in 1-5 years
4 | Likely | May occur annually
5 | Very Likely | Expected to occur frequently
IMPACT SCALE
Score | Level | Description
1 | Very Low | Minor disruption, negligible financial impact
2 | Low | Limited disruption, minor financial impact, no safety impact
3 | Medium | Moderate disruption, significant financial impact, minor safety impact
4 | High | Major disruption, severe financial impact, moderate safety impact
5 | Critical | Catastrophic disruption, extreme financial loss, severe safety impact
RISK SCORE MATRIX (Score = Likelihood × Impact)
Score Range | Risk Level | Escalation Path
1-2 | Very Low | Managed at Operational Team Level
3-4 | Low | Managed by System / Asset Owner
5-10 | Medium | Escalate to Head of Department / Risk Management Team
12-16 | High | Escalate to C-Suite (CEO / CRO / CISO) via the GRC Committee
20-25 | Critical | Escalate to the Board of Directors via the Enterprise Risk Register

## Risk Assessment Matrix
RISK ASSESSMENT MATRIX (5 × 5)
Risk Score = Likelihood × Impact ¦ Range: 1 – 25
Likelihood ↓ / Impact → | 1 Very Low | 2 Low | 3 Medium | 4 High | 5 Critical
5 – Very High | 5 MEDIUM | 10 MEDIUM | 15 HIGH | 20 CRITICAL | 25 CRITICAL
4 – High | 4 LOW | 8 MEDIUM | 12 HIGH | 16 HIGH | 20 CRITICAL
3 – Medium | 3 LOW | 6 MEDIUM | 9 MEDIUM | 12 HIGH | 15 HIGH
2 – Low | 2 VERY LOW | 4 LOW | 6 MEDIUM | 8 MEDIUM | 10 MEDIUM
1 – Very Low | 1 VERY LOW | 2 VERY LOW | 3 LOW | 4 LOW | 5 MEDIUM
RISK LEVEL LEGEND
🔴 CRITICAL | Score 20–25 | Escalate to Board of Directors via Enterprise Risk Register (ERR)
🟠 HIGH | Score 12–16 | Escalate to C-Suite (CEO / CRO / CISO) via GRC Committee
🟡 MEDIUM | Score 5–10 | Escalate to Head of Department / Risk Management Team
🟢 LOW | Score 3–4 | Managed by System / Asset Owner
🔵 VERY LOW | Score 1–2 | Managed at Operational Team Level

## Risk Heat Map
RISK HEAT MAP — WADJET GRC
Risks plotted by Likelihood × Impact ¦ Hover a cell to see assigned Risk IDs
Likelihood ↓ / Impact → | 1 Very Low | 2 Low | 3 Medium | 4 High | 5 Critical | Risk IDs
5 – Very High | · | · | · | R-001 | · | R-001
4 – High | · | · | · | · | R-002 R-029 R-031 R-032 R-036 R-042 R-047 | R-002, R-029, R-031, R-032, R-036, R-042, R-047
3 – Medium | · | · | · | R-004 R-007 | · | R-004, R-007
2 – Low | · | · | · | · | · | —
1 – Very Low | · | · | · | · | · | —
HEAT MAP COLOUR KEY
🔴 CRITICAL (20–25)
🟠 HIGH (12–16)
🟡 MEDIUM (5–10)
🟢 LOW (3–4)
🔵 VERY LOW (1–2)

## Summary Dashboard
WADJET GRC — EXECUTIVE RISK SUMMARY DASHBOARD
As of: June 2026 ¦ Total: 48 Risks ¦ Critical: 11 ¦ High: 34 ¦ Total Budget: $4.275M ¦ Est. Loss Prevented: $109M
RISK BREAKDOWN BY CATEGORY
# | Category | Total Risks | Critical | High | Medium | Budget | Est. Loss | Red RAG | Amber RAG
1 | Compliance & Legal | 9 | 3 | 6 | 0 | $485K | $15.5M | 3 | 2
2 | Cybersecurity | 7 | 3 | 4 | 0 | $980K | $16.5M | 4 | 1
3 | Information Security | 6 | 0 | 6 | 0 | $665K | $15.5M | 3 | 1
4 | Operational & BCP | 6 | 1 | 4 | 1 | $625K | $16.5M | 3 | 1
5 | Human Risk | 4 | 1 | 3 | 0 | $260K | $7M | 1 | 2
6 | Third Party | 5 | 0 | 5 | 0 | $410K | $12M | 1 | 2
7 | Application Security & Mobile | 3 | 1 | 2 | 0 | $290K | $6.5M | 1 | 0
8 | Cloud, Physical & AI | 4 | 2 | 2 | 0 | $500K | $12M | 1 | 2
9 | Risk Management & GRC | 2 | 0 | 2 | 0 | $60K | $1.5M | 0 | 0
| TOTAL | 46 | 11 | 34 | 1 | $4.275M | $109M | 13 | 11
RAG STATUS SUMMARY
🔴 Red — Immediate Action Required |  |  | 13 Risks |  | Escalate to CISO / Risk Committee immediately
🟡 Amber — Monitor Closely |  |  | 11 Risks |  | Review progress weekly; escalate if no improvement
🟢 Green — On Track |  |  | 24 Risks |  | Continue monitoring per review schedule